## Prioritization
mvps | status | description | person | due date | estimate | start date
abc-123 |  | abc feature | Mario |  | 10 | 2024-06-03
xyz-321 |  | xyz feature | Peach |  | 20 | 2024-06-14
epics
android-123 |  | android | Peach |  | 15 | 2024-05-28
ios-321 |  | ios | Luigi |  | 20 | 2024-07-01
web-42 |  | web | Yoshi |  | 60 | 2024-07-01
spike-333 |  | spike | Mario |  | 30 | 2024-06-19

## Timeline
| TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
| 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27
Luigi | [24 empty] | ios | ios | ios | ios | ios
Mario |  |  |  |  | abc feature | abc feature | abc feature
Mario | [16 empty] | spike | spike | spike | spike | spike | spike | spike | spike
Peach | android | android | android | android | android
Peach | [13 empty] | xyz feature | xyz feature | xyz feature | xyz feature | xyz feature | xyz feature | xyz feature
Yoshi | [24 empty] | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web | web

## People
Mario | 4
Luigi | 4
Peach | 3
Yoshi | 2